## Tabelle1
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 2022-04-22
Group Number |  | 7
Participant 1 |  | Marcel Sziner
Participant 2 |  | Skyler Mayfield
Participant 3 |  | Max Ornik
Participant 4 |  | Marin Josic
Participant 5 |  | Sara Grmaca
Mentor |  | Manuel-Christopher Parg
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Discussing basic css structure | 1 | 1 | 0 | 1
2 | Document requirements | 2 | 4 | 2 | 1
3 | Basic layout (files, directory, structure) | 1 | 1 | 0 | 1
4 | implement functionality to draw in canvas (images, text, ...) | 2 | 1 | -1 | 1
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 1 | 4 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol