## Tabelle1
Sprint Review Protocol
Sprint No: |  | 6
Date & Time |  | 2022-06-21
Group Number |  | 7
Participant 1 |  | Marcel Sziener
Participant 2 |  | Skyler Mayfield
Participant 3 |  | Max Ornik
Participant 4
Participant 5
Mentor |  | Manuel-Christopher Parg
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Effort [h] | Priority | Delta [h] | Passed | failed | remarks
1 | Implement Controller Object for Key Handling | 1 | 2 | Medium | 1 | 1
2 | Implement Character Movement | 2 | 6 | High | 4 | 1
3 | Create Character Object | 2 | 4 | High | 2 | 1
4 | Create Player Object | 2 | 4 | High | 2 | 1
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
14 |  |  |  |  | 9 | 4 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planning tool to this protocol