## Tabelle1
Sprint Review Protocol
Sprint No: |  | 7
Date & Time |  | 2022-07-05
Group Number |  | 7
Participant 1 |  | Marcel Sziener
Participant 2 |  | Skyler Mayfield
Participant 3 |  | Max Ornik
Participant 4
Participant 5
Mentor |  | Manuel-Christopher Parg
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Effort [h] | Priority | Delta [h] | Passed | failed | remarks
1 | Create enemy object | 3 | 5 | high | 2 | 1
2 | Make levels | 3 | 8 | High | 5 | 1
3 | Discuss combat plan | 1 | 1 | High | 0 | 1
4 | Create Player Object | 2 | 4 | High | 2 | 1
5 | Create classes for world tiles | 2 | 2 | medium | 0 | 1
6 | Add world boundary logic | 1 | 1 | low | 0 | 1
7 | Write documentation | 2 | 4 | high | 2 | 1
8 | Create presentation slides | 1 | 1 | high | 3 | 1
9 | Create presentation video | 3 | 6 | high | 0 | 1
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
14 |  |  |  |  | 14 | 9 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planning tool to this protocol